## Sheet1
Team Name: | Project Z-Code |  | Remaining Work |  | Note:
| Ian Lamb / Derek Brown |  | Planned | To Complete | Planned and Time To Complete can be in story points or hours.
|  |  | 30 |  | Update at the end of each week with time remaining to complete Sprint activities
| Sprint 1 | Sept. 24 | 20 | 20
|  | Oct. 1 | 10 | 14
|  | Oct. 9 | 0 | 0
30
| Sprint 2 | Oct. 15 | 20
|  | Oct. 22 | 10
|  | Oct. 30 | 0
40
| Sprint 3 | Nov. 5 | 30
|  | Nov. 12 | 20
|  | Nov. 19 | 10
|  | Nov. 27 | 0
Planned and Time To Complete can be in story points or hours.